## Documents
Approx. Date | Contents | Artifact | SDLC/Project Stage | Status
25/07/2026 | Topic selected/research | Overview & Research | Initiation | Completed
27/07/2026 | Initial project draft | Draft PDF | Planning | Completed
30/07/2026 | Streamlit prototype | UI 1–3 | Prototype | Completed
18/08/2026 | Architecture | Architecture | Design | Completed
18/08/2026 | Acceptance criteria+SDLC+users | Architecture & Approach | Analysis/Design | Completed
19/08/2026 | Use case diagram | Use Case Diagram | Requirements | Completed
21/08/2026 | Requirements analysis | Requirements Analysis | Requirements | Pending Review
21/08/2026 | Project Plant excel sheet | Project Plan | Planning | Pending Review
27/08/2026 | Primitive document for EDA | Data Analysis Draft | Design | Pending Review

## Project Plan
Milestone ID | Milestone Name | Objective | Start Date | Target End Date | Actual End Date | Demo Date | Status | Review
M1 | Project Research and Scope | Define problem, scope, users and proposed solution | 27/07/2026 | 29/07/2026 | 29/07/2026 | None To Demo | Completed | Completed
M2 | Intital Prototype | Validate feasibility through initial Streamlit prototype | 27/07/2026 | 31/07/2026 | 31/07/2026 | None To Demo | Completed | Completed
M3 | Core Implementation | Implement application framework and core preprocessing modules, with 1 full cycle of basic operations | 30/07/2026 | 14/8/2026 | 13/8/2026 | 17/08/2026 | Completed | Completed
M4 | System Analysis and Requirements | Establish architecture, requirements, acceptance criteria, use cases and SDLC approach | 18/8/2026 | 21/07/2026 | 21/07/2026 | 24/08/2026 | Completed | Completed
M5 | Advance Implementation | Implement remaining preprocessing capabilities along with analysis | 24/08/2026 | 2026-04-09 | 2026-04-09 | 2026-04-09 | Completed | Completed
M6 | Scalability Features | Investigate and prototype large-dataset processing | 2026-07-09 | 25/09/2026 | 29/05/2026 | 2026-01-10 | Completed | Completed | Note: Need to learn 2 new technologies for this milestone, so tentatively allocating 3 weeks. Also festive events are present which may unexpected alter the schedule
M7 | Testing and finalize | Testing of each module and full system testing, documention | 2026-05-10 | 23/10/2026 | TBD | TBD | In Progress | Pending Review | Note: Testing may take a while longer, also college related contents will be present during this period. Allocating way more time here, but there exists a possiblity of early completion
M8 | Advance Scope | Experiment on AI features, automation, extension/plugin creation | TBD | TBD | TBD | TBD | Not Planned | Not Started | Remaining time (half october + 15 days of november) can be allocated to working on advance scope (future scope). The project's main scope will have already finished.

## M1
Project Research and Scope
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Comments | Delay Reason | Revised Target Date | Delay Recovery
M1T1 | Research Problem statement | Find out information about the problem and how it can be solved | Dhruva | 30/07/2026 | Completed | 28/07/2026 | NA | Considered a Summary project. Ruled out the summary project due to limited scope | - | - | -
M1T2 | Identify Real world issues | Research what are the main issues faced by people who want a similar system | Dhruva | 30/07/2026 | Completed | 28/07/2026 | Problem Statement | Considered a Summary project. Ruled out the summary project due to limited scope | - | - | -
M1T3 | Research existing solutions | Identify the current solutions and how they can be improved | Dhruva | 30/07/2026 | Completed | 28/07/2026 | Problem Statement | Performed comparative analysis between several data preprocessing platforms | - | - | -
M1T4 | Define project objective | Define the goals and what niche the project will fill | Dhruva | 30/07/2026 | Completed | 28/07/2026 | Problem Statement | Understood the use of the project in real world | - | - | -
M1T5 | Define initial scope | Define what can be done comfortably in the duration of the project | Dhruva | 30/07/2026 | Completed | 28/07/2026 | Existing Solutions | Defined what can be done earlist as a MVP for the project | - | - | -
M1T6 | Identify target users | Reseach which type and profession of people are most likely to use the system | Dhruva | 30/07/2026 | Completed | 29/07/2026 | Problem Statement | Discussed and narrowed down the target users and ruled out non-technical users | - | - | -
M1T7 | Define expected input and output | Define the dataset parameters and how the final output dataframe would look like | Dhruva | 30/07/2026 | Completed | 29/07/2026 | Target Users | Several ideations over how the dataset in and out would work | - | - | -
M1T8 | Prepare intial project Draft | Create a draft of all of the above into a single document | Dhruva | 30/07/2026 | Completed | 29/07/2026 | All of Above | Created a draft, had issues with title and future scope. Rewrote those sections | - | - | -

## M2
Intital Prototype
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Comments | Delay Reason | Revised Target Date | Delay Recovery
M2T1 | Create initial Streamlit application | Create a single page trial application to understand modular building method | Dhruva | 28/07/2026 | Completed | 27/07/2026 | Draft of project | Tried several layouts for streamlit, finalized a drop down based GUI | - | - | -
M2T2 | Implement basic dataset upload | Implement function to upload CSV datasets of upto 200MB | Dhruva | 28/07/2026 | Completed | 27/07/2026 | Draft of project | Used streamlit in built functions to get a drag and drop UI | - | - | -
M2T3 | Create initial UI | Create streamlit based UI with drop down work flow | Dhruva | 29/07/2026 | Completed | 28/07/2026 | Draft of project, Workflow diagram | Built the initial UI with help of Chatgpt and streamlit documentations | - | - | -
M2T4 | Test basic preprocessing workflow | Create logics for basic operations and simulate a run | Dhruva | 29/07/2026 | Completed | 28/07/2026 | Draft of project, Workflow diagram | Implemented small operations and tried them out on diabetes dataset | - | - | -
M2T5 | Prepare sample dataset | Modify dataset such as to fit the preprocessing steps and create visible and testable results | Dhruva | 31/07/2026 | Completed | 31/07/2026 | Dataset | Modified the diabetes dataset to increase the impurity | - | - | -
M2T6 | Evaluate feasibility of Streamlit approach | Understand how feasible it is to use Streamlit as a backbone for the project | Dhruva | 31/07/2026 | Completed | 31/07/2026 | All of Above | Checked how good of an application this can be if it made out into the world | - | - | -

## M3
Core Implementation
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Comments | Delay Reason | Revised Target Date | Delay Recovery
M3T1 | Finalize project structure | Finalize the file and project structure to build upon | Dhruva | 2026-03-08 | Completed | 2026-03-08 | Prototype interface | Experimented with a single file structure but ruled it out due to complexity | - | - | -
M3T2 | Implement session management | Make sure only 1 dataframe is being used all the time | Dhruva | 2026-04-08 | Completed | 2026-04-08 | Memory Handling | Implemented 1 dataframe session management as a modular session file | - | - | -
M3T3 | Implement dataset loader,preview and quick summary | Basic data loading and summary operations | Dhruva | 2026-04-08 | Completed | 2026-04-08 | Prototype interface | Summary failed a few times till the function was written to output onto streamlit | - | - | -
M3T4 | Implement registry based module architecture | Modular, metadata based retrival approach | Dhruva | 2026-06-08 | Completed | 2026-04-08 | Prototype interface | Finalized the modular approach since it can help to add and remove features later on | - | - | -
M3T5 | Implement missing values,duplicates,trial export | Initial 3 modules, of which export trial was important | Dhruva | 2026-06-08 | Completed | 2026-04-08 | Workflow Diagram | Made 3 basic operations to check if the platform works properly | - | - | -
M3T6 | Implement white space,invalid data types | Trim whitespace and handle invalid data types in wrong columns | Dhruva | 14/08/2026 | Completed | 13/08/2026 | Workflow Diagram | Made sure that string data was made uniform | - | - | -
M3T7 | Implement Full export | Make sure each dataframe output is consistent | Dhruva | 14/08/2026 | Completed | 13/08/2026 | Draft of project | As per the project description CSV and XLSX are options, but realistically people would use CSV more | - | - | -
M3T8 | Implement extra preprocessing | Handle outliers,casing and redundancy gracefully | Dhruva | 14/08/2026 | Completed | 13/08/2026 | Prototype interface | Implemented these as a part of extra preprocessing because not large enough to have a separate milestone | - | - | -

## M4
System Analysis and Requirements
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Comments | Delay Reason | Revised Target Date | Delay Recovery
M4T1 | Define high-level architecture | Define a layout of the high level working of the system | Dhruva | 18/08/2026 | Completed | 18/08/2026 | Draft of project | With help from AI found out how to abstract the system to high level architecture | - | - | -
M4T2 | Define system components | Define what all system components will be implemented | Dhruva | 18/08/2026 | Completed | 18/08/2026 | Architecture | Broke the system to root components, very detailed at first but then abstracted | - | - | -
M4T3 | Define acceptance criteria | Define what qualifies the system to accepted based on rules and requirements | Dhruva | 18/08/2026 | Completed | 18/08/2026 | Draft of project | With help from AI wrote some acceptance scenarios for the use cases, took lot of rewriting | - | - | -
M4T4 | Define non-functional requirements | Define non functional heurstic expectation from the system | Dhruva | 19/08/2026 | Completed | 18/08/2026 | Architecture | - | - | - | -
M4T5 | Define SDLC approach | Define how the project will use SDLC in its lifetime | Dhruva | 19/08/2026 | Completed | 18/08/2026 | Logical flow of the system | - | - | - | -
M4T6 | Identify target users | Understand who will use the system and how | Dhruva | 19/08/2026 | Completed | 18/08/2026 | Draft of project | - | - | - | -
M4T7 | Create use case diagram | Define what use cases the system should satify given the user requirements | Dhruva | 19/08/2026 | Completed | 19/08/2026 | Architecture | Created a basic UML diagram for clear real world use and how the users will use it | - | - | -
M4T8 | Prepare requirements analysis | Perform requirement analysis in depth | Dhruva | 21/08/2026 | Completed | 21/08/2026 | Architecture and Approach | With help from AI, wrote several requirements analysis sections, required lot of rewriting and reworking to make it fit the project | - | - | -
M4T9 | Define functional requirements | Define requirements which work at root level of the system | Dhruva | 21/08/2026 | Completed | 21/08/2026 | Architecture and Approach | - | - | - | -
M4T10 | Define preprocessing requirements | Define the specific module based requirements | Dhruva | 21/08/2026 | Completed | 21/08/2026 | Architecture and Approach | - | - | - | -

## M5
Advance Implementation
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Comments | Delay Reason | Revised Target Date | Delay Recovery
M5T1 | Formatting normalization | Textual clean up for each module | Dhruva | 27/08/2026 | Completed | 24/08/2026 | NA | Cleaned up the textual contents of code for each module to make it easy to read | - | - | -
M5T2 | Encoding | Implement encoding for textual data | Dhruva | 27/08/2026 | Completed | 24/08/2026 | Basic Preprocessing | Settled for 2 encoding methods instead of every single method, this will help to keep testing in bounds | - | - | -
M5T3 | Scaling | Scale the numeric data with 2 methods | Dhruva | 28/08/2026 | Completed | 26/08/2026 (full) | Basic Preprocessing | Settled for 2 scaling methods instead of just 1 minmax, having option of 2 helps to target specific columns better | - | - | -
M5T4 | Normalization | Normalize the numeric data with zscore (standardscaler) | Dhruva | 28/08/2026 | Completed | 26/08/2026 (major) | Basic Preprocessing | As most data needs to be normalized, standardscaler was a good idea instead of manually writing maths code | - | - | -
M5T5 | Correlation analysis | Create heatmap and p values for PCC method and handle dropping columns | Dhruva | 2026-01-09 | Completed | 31/08/2026 (major) | Statistical understanding, basic preprocessing | Researching how heatmaps can be displayed properly on streamlit. Trial and error about how to render the image
M5T6 | Analysis Modules | Major section, implement EDA contents | Dhruva | 2026-04-09 | Completed | 04/09/2026 (major) | Dataset loading, Basic Preprocessing | Added an extra section, which I later got to know, I should not be doing as this expands the scope, should have added this in the initial draft itself. Implemented basic info,pcc,null count. Added 2 sections (describe and value counts) they took lot of logical working | - | - | - | new need, yet to be discussed
M5T7 | Additional validation | Make sure the modules work in properly set logical flow (wrong flow might lead to data quality damage) | Dhruva | 2026-04-09 | Completed | 2026-02-09 | All of Above | Researched the best flow for linear preprocessing and made sure the modules are structured like that | - | - | -

## M6
(Tentative Dates) Scalability Features
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Comments | Delay Reason | Revised Target Date | Delay Recovery
M6T1 | Learn basics of DuckDB | Learn and understand how to implement DuckDB | Dhruva | 2026-10-09 | Completed | 2026-10-09 | NA | Learning DuckDB as a technology is important to implement large dataset loading | - | - | -
M6T2 | Implement chunking using DuckDB and learn parquet | Implement basic operation of viewing 10 records, selecting rows based on conditions | Dhruva | 2026-11-09 | Completed | 2026-11-09 | All of Above | Simple operation to view recording using python duckdb sql helps to understand how to use duckdb for this project | - | - | -
M6T3 | Trial of large dataset | Try out loading large datasets using duckdb and see if the scaling works (separate file, not app.py) | Dhruva | 15/09/2026 | Completed | 15/09/2026 | All of Above | try out (9gb csv - duckdb - query) | - | - | -
M6T4 | Introduce data manger and rewrite app.py | Introduce data manager concept to handle large and small datasets individually, rewrite sections of app.py to reflect this data difference | Dhruva | 22/09/2026 | Completed | 22/09/2026 | All of Above | if size less than thres then pandas, else duckdb+parquet, largest change till date. Research on how to implement data manager layers | - | - | -
M6T5 | Migrate few of the current operations | info,describe etc along with checking for export | Dhruva | 23/09/2026 | Completed | 25/09/2026 | All of Above | Will mostly need work over the weekend as well to fit into schedule properly | Complications with respect to DuckDB and Streamlit data handling | 25/09/2026 | Scope adjustment,reevaluate the target functionality
M6T6 | Migrate information/analysis operations, and export | remove redundant columns,remove duplicates,trim whitespaces,handle casing,missing values | Dhruva | 25/09/2026 | Completed | 29/09/2026 | M6T4,M6T6 | Will mostly need extra work compared to pandas as this requires SQL contents | Above | 29/09/2026 | Scope adjustment,reevaluate the target functionality

## M7
Testing
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Comments | Delay Reason | Revised Target Date | Delay Recovery
M7T1 | Test module and scenario decision | Decide primary contents for what to test and what sections to test | Dhruva | 2026-07-10 | Completed | 2026-07-10 | Finish M6 | Decide based test scenarios and what modules to test | - | - | -
M7T2 | Manual and automated testing (pytest?) | Learn basic pytest and also try out manual testing | Dhruva | 2026-09-10 | Completed | 2026-09-10 | M7T1 | Trial testing scripts for pytest and checkout manual practices for testing | - | - | -
M7T3 | Unit Testing | Each module seperately tested | Dhruva | 14/10/2026 | Completed | 14/10/2026 | All of Above | File by file testing for each module and script | - | - | -
M7T4 | Integration Testing | Combine modules under 1 functionality and test | Dhruva | 20/10/2026 | Completed | 19/10/2026 | All of Above | Check integration between 2 modules main for analysis section,perform manually | - | - | -
M7T5 | Full dataset run and Report | Run full dataset pipeline, and compile a small report of test passing and failing | Dhruva | 23/10/2026 | In Progress | - | All of Above | Full run of dataset along with a sheet or report for testing section | - | - | -