## Documents
Approx. Date | Contents | Artifact | SDLC/Project Stage | Status
25/07/2026 | Topic selected/research | Overview & Research | Initiation | Completed
27/07/2026 | Initial project draft | Draft PDF | Planning | Completed
30/07/2026 | Streamlit prototype | UI 1–3 | Prototype | Completed
18/08/2026 | Architecture | Architecture | Design | Completed
18/08/2026 | Acceptance criteria+SDLC+users | Architecture & Approach | Analysis/Design | Completed
19/08/2026 | Use case diagram | Use Case Diagram | Requirements | Completed
21/08/2026 | Requirements analysis | Requirements Analysis | Requirements | Pending Review

## Project Plan
Milestone ID | Milestone Name | Objective | Start Date | Target End Date | Actual End Date | Demo Date | Status | Review
M1 | Project Research and Scope | Define problem, scope, users and proposed solution | 27/07/2026 | 29/07/2026 | 29/07/2026 | NA | Completed | Completed
M2 | Intital Prototype | Validate feasibility through initial Streamlit prototype | 27/07/2026 | 31/07/2026 | 31/07/2026 | NA | Completed | Completed
M3 | Core Implementation | Implement application framework and core preprocessing modules, with 1 full cycle of basic operations | 30/07/2026 | 14/8/2026 | 13/8/2026 | 17/08/2026 | Completed | Completed
M4 | System Analysis and Requirements | Establish architecture, requirements, acceptance criteria, use cases and SDLC approach | 18/8/2026 | 21/07/2026 | 21/07/2026 | 24/08/2026 | Completed | Pending Review
M5 | Advance Implementation | Implement remaining preprocessing capabilities along with analysis | 24/08/2026 | 2026-04-09 | - | - | In Progress | TBD
M6 | Scalability | Investigate and prototype large-dataset processing | TBD | TBD | TBD | TBD | Not Started | TBD
M7 | Testing and finalize | Testing of each module and full system testing, documention | TBD | TBD | TBD | TBD | Not Started | TBD
M8 | Advance Scope | Experiment on AI features, automation, extension/plugin creation | TBD | TBD | TBD | TBD | Not Planned | TBD

## M1
Project Research and Scope
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Delay Reason | Revised Target Date | Delay Recovery
M1T1 | Research Problem statement | Find out information about the problem and how it can be solved | Dhruva | 30/07/2026 | Completed | 28/07/2026 | NA | - | - | -
M1T2 | Identify Real world issues | Research what are the main issues faced by people who want a similar system | Dhruva | 30/07/2026 | Completed | 28/07/2026 | Problem Statement | - | - | -
M1T3 | Research existing solutions | Identify the current solutions and how they can be improved | Dhruva | 30/07/2026 | Completed | 28/07/2026 | Problem Statement | - | - | -
M1T4 | Define project objective | Define the goals and what niche the project will fill | Dhruva | 30/07/2026 | Completed | 28/07/2026 | Problem Statement | - | - | -
M1T5 | Define initial scope | Define what can be done comfortably in the duration of the project | Dhruva | 30/07/2026 | Completed | 28/07/2026 | Existing Solutions | - | - | -
M1T6 | Identify target users | Reseach which type and profession of people are most likely to use the system | Dhruva | 30/07/2026 | Completed | 29/07/2026 | Problem Statement | - | - | -
M1T7 | Define expected input and output | Define the dataset parameters and how the final output dataframe would look like | Dhruva | 30/07/2026 | Completed | 29/07/2026 | Target Users | - | - | -
M1T8 | Prepare intial project Draft | Create a draft of all of the above into a single document | Dhruva | 30/07/2026 | Completed | 29/07/2026 | All of Above | - | - | -

## M2
Intital Prototype
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Delay Reason | Revised Target Date | Delay Recovery
M2T1 | Create initial Streamlit application | Create a single page trial application to understand modular building method | Dhruva | 28/07/2026 | Completed | 27/07/2026 | Draft of project | - | - | -
M2T2 | Implement basic dataset upload | Implement function to upload CSV datasets of upto 200MB | Dhruva | 28/07/2026 | Completed | 27/07/2026 | Draft of project | - | - | -
M2T3 | Create initial UI | Create streamlit based UI with drop down work flow | Dhruva | 29/07/2026 | Completed | 28/07/2026 | Draft of project, Workflow diagram | - | - | -
M2T4 | Test basic preprocessing workflow | Create logics for basic operations and simulate a run | Dhruva | 29/07/2026 | Completed | 28/07/2026 | Draft of project, Workflow diagram | - | - | -
M2T5 | Prepare sample dataset | Modify dataset such as to fit the preprocessing steps and create visible and testable results | Dhruva | 31/07/2026 | Completed | 31/07/2026 | Dataset | - | - | -
M2T6 | Evaluate feasibility of Streamlit approach | Understand how feasible it is to use Streamlit as a backbone for the project | Dhruva | 31/07/2026 | Completed | 31/07/2026 | All of Above | - | - | -

## M3
Core Implementation
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Delay Reason | Revised Target Date | Delay Recovery
M3T1 | Finalize project structure | Finalize the file and project structure to build upon | Dhruva | 2026-03-08 | Completed | 2026-03-08 | Prototype interface | - | - | -
M3T2 | Implement session management | Make sure only 1 dataframe is being used all the time | Dhruva | 2026-04-08 | Completed | 2026-04-08 | Memory Handling | - | - | -
M3T3 | Implement dataset loader,preview and quick summary | Basic data loading and summary operations | Dhruva | 2026-04-08 | Completed | 2026-04-08 | Prototype interface | - | - | -
M3T4 | Implement registry based module architecture | Modular, metadata based retrival approach | Dhruva | 2026-06-08 | Completed | 2026-04-08 | Prototype interface | - | - | -
M3T5 | Implement missing values,duplicates,trial export | Initial 3 modules, of which export trial was important | Dhruva | 2026-06-08 | Completed | 2026-04-08 | Workflow Diagram | - | - | -
M3T6 | Implement white space,invalid data types | Trim whitespace and handle invalid data types in wrong columns | Dhruva | 14/08/2026 | Completed | 13/08/2026 | Workflow Diagram | - | - | -
M3T7 | Implement Full export | Make sure each dataframe output is consistent | Dhruva | 14/08/2026 | Completed | 13/08/2026 | Draft of project | - | - | -
M3T8 | Implement extra preprocessing | Handle outliers,casing and redundancy gracefully | Dhruva | 14/08/2026 | Completed | 13/08/2026 | Prototype interface | - | - | -

## M4
System Analysis and Requirements
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Delay Reason | Revised Target Date | Delay Recovery
M4T1 | Define high-level architecture | Define a layout of the high level working of the system | Dhruva | 18/08/2026 | Completed | 18/08/2026 | Draft of project | - | - | -
M4T2 | Define system components | Define what all system components will be implemented | Dhruva | 18/08/2026 | Completed | 18/08/2026 | Architecture | - | - | -
M4T3 | Define acceptance criteria | Define what qualifies the system to accepted based on rules and requirements | Dhruva | 18/08/2026 | Completed | 18/08/2026 | Draft of project | - | - | -
M4T4 | Define non-functional requirements | Define non functional heurstic expectation from the system | Dhruva | 19/08/2026 | Completed | 18/08/2026 | Architecture | - | - | -
M4T5 | Define SDLC approach | Define how the project will use SDLC in its lifetime | Dhruva | 19/08/2026 | Completed | 18/08/2026 | Logical flow of the system | - | - | -
M4T6 | Identify target users | Understand who will use the system and how | Dhruva | 19/08/2026 | Completed | 18/08/2026 | Draft of project | - | - | -
M4T7 | Create use case diagram | Define what use cases the system should satify given the user requirements | Dhruva | 19/08/2026 | Completed | 19/08/2026 | Architecture | - | - | -
M4T8 | Prepare requirements analysis | Perform requirement analysis in depth | Dhruva | 21/08/2026 | Completed | 21/08/2026 | Architecture and Approach | - | - | -
M4T9 | Define functional requirements | Define requirements which work at root level of the system | Dhruva | 21/08/2026 | Completed | 21/08/2026 | Architecture and Approach | - | - | -
M4T10 | Define preprocessing requirements | Define the specific module based requirements | Dhruva | 21/08/2026 | Completed | 21/08/2026 | Architecture and Approach | - | - | -

## M5
Advance Implementation
Task ID | Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependancy | Delay Reason | Revised Target Date | Delay Recovery
M5T1 | Formatting normalization | Textual clean up for each module | Dhruva | 27/08/2026 | Completed | 24/08/2026 | NA | - | - | -
M5T2 | Encoding | Implement encoding for textual data | Dhruva | 27/08/2026 | Completed | 24/08/2026 | Basic Preprocessing | - | - | -
M5T3 | Scaling | Scale the numeric data with 2 methods | Dhruva | 28/08/2026 | Completed | 26/08/2026 (full) | Basic Preprocessing | - | - | -
M5T4 | Normalization | Normalize the numeric data with 2 methods | Dhruva | 28/08/2026 | In progress | 26/08/2026 (major) | Basic Preprocessing | - | - | -
M5T5 | Correlation analysis | Create heatmap and p values for PCC method and handle dropping columns | Dhruva | 2026-01-09 | In progress | - | Statistical understanding, basic preprocessing
M5T6 | Analysis Modules | Large section, implement EDA contents | Dhruva | 2026-04-09 | Not Started |  | Dataset loading, Basic Preprocessing | - | - | - | new need, yet to be discussed
M5T7 | Additional validation | Make sure the modules work in properly set logical flow (wrong flow might lead to data quality damage) | Dhruva | 2026-04-09 | In progress | - | All of Above | - | - | -